## Intervention Tracker
| Company Name | HyperLaunch Private Limited
| Program Name | Data Analytics and Visualization
| Last Updated Date | 2026-02-02
| Intervention | 1=2.5 hours Intervention | [6 empty] | Week - 1 | [5 empty] | Week - 2 | [5 empty] | Week - 3 | [5 empty] | Week - 4 | [5 empty] | Week - 5 | [5 empty] | Week - 6 | [5 empty] | Week - 7 | [5 empty] | Week - 8 | [5 empty] | Week - 9 | [5 empty] | Completion Status - In hours |  |  |  |  | Completion Status - Interventions
Sl. No | University Code | College Name | Start Date | End Date | Timing | Batch Size | Students Count | Trainer name | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Total Program Hours Per Batch | Batch Wise Weekly hours Completed | Overall Completed Hours | Pending Hours Per Batch | Total Hours | Intervention Completed | Pending Intervention | Completeion Percentage
1 | unm1473 | ST. THOMAS COLLEGE OF ARTSand SCIENCE, KOYAMBEDU | 2026-01-05 | 2026-03-12 | 8.40 AM - 11.10AM | 5.9 | 54 | Kiruthiga | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 | [5 empty] | 1 |  | 1 | [35 empty] | 45 | 15 | 80 | 30 | 315 | 6 | 12 | 33.33%
[5 empty] | 8.40 AM - 11.10AM |  | 53 | Bhavani | 1 | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1 | [35 empty] | 45 | 12.5 |  | 32.5 |  | 5 | 13 | 27.78%
[5 empty] | 8.40 AM - 11.10AM |  | 53 | Madhan |  | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1 | 1 | [39 empty] | 45 | 12.5 |  | 32.5 |  | 5 | 13 | 27.78%
[5 empty] | 8.40 AM - 11.10AM |  | 51 | Pugazh |  |  | 1 | 1 |  |  |  |  | 1 | [5 empty] | 1 | 1 | [38 empty] | 45 | 12.5 |  | 32.5 |  | 5 | 13 | 27.78%
[5 empty] | 8.40 AM - 11.10AM |  | 51 | Nikileshwari |  |  |  | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1 | 1 | [37 empty] | 45 | 12.5 |  | 32.5 |  | 5 | 13 | 27.78%
[5 empty] | 1:30–4:00 |  | 48 | Angel | 1 | 1 |  |  |  |  | 1 | [47 empty] | 45 | 7.5 |  | 37.5 |  | 3 | 15 | 16.67%
[7 empty] | 48 | Subhash | 1 | 1 |  |  |  |  | 1 | [47 empty] | 45 | 7.5 |  | 37.5 |  | 3 | 15 | 16.67%
2 | unm1741 | ARULMIGU KAPALEESWARAR ARTS AND SCIENCE COLLEGE, KOLATHUR | 2026-01-05 | 2026-03-16 | 9-11.30am | 1.58 | 50 | Madhan | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  | 1 | [29 empty] | 45 | 17.5 | 35 | 27.5 | 90 | 7 | 11 | 38.89%
[5 empty] | 11.30 -2pm |  | 45 | Pugazh | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  | 1 | [29 empty] | 45 | 17.5 |  | 27.5 |  | 7 | 11 | 38.89%
3 | unm1363 | VALLIAMMAL COLLEGE FOR WOMEN, ANNA NAGAR EAST | 2026-01-06 | 2026-03-12 | 8.30 - 11am | 3.2 | 96 | Priyadharshini |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  |  | 1 | [35 empty] | 45 | 17.5 | 35 | 27.5 | 90 | 7 | 11 | 38.89%
[5 empty] | 12:00 pm to 2:30 pm |  | 48 | Harini |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  |  | 1 | [35 empty] | 45 | 17.5 |  | 27.5 |  | 7 | 11 | 38.89%
[7 empty] | 49 | Hema
4 | unm1351 | CHEVALIER T. THOMAS ELIZABETH COLLEGE FOR (W), SEMBIUM | 2026-01-06 | 2026-03-12 | 9:30 AM – 12:00 PM | 2.3 | 47 | Atchaya |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [38 empty] | 45 | 15 | 45 | 30 | 135 | 6 | 12 | 33.33%
[5 empty] | 12:30 PM – 3:00 PM |  | 46 |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [38 empty] | 45 | 15 |  | 30 |  | 6 | 12 | 33.33%
[5 empty] | 12:30 PM – 3:00 PM |  | 49 |  | 1 | 1 |  |  |  |  | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1 | [35 empty] | 45 | 15 |  | 30 |  | 6 | 12 | 33.33%
5 | unm203 | K.C.S. KASI NADAR COLLEGE OF ARTS AND SCIENCE | 2026-01-06 | 2026-03-11 | 9 am to 11:30 am | 2.3 | 138 | Nagadinesh |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [39 empty] | 45 | 15 | 30 | 30 | 90 | 6 | 12 | 33.33%
[5 empty] | 12 pm to 2 pm |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [39 empty] | 45 | 15 |  | 30 |  | 6 | 12 | 33.33%
6 | unm1483 | ANNAI VEILANKANNI'S COLLEGE FOR WOMEN | 2026-01-05 | 2026-03-16 | 8.45 to 11.15 | 1.3 | 40 | Angel |  | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | [35 empty] | 45 | 15 | 30 | 30 | 90 | 6 | 12 | 33.33%
[5 empty] | 11.45 to 2.15 |  | 38 |  |  | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | [35 empty] | 45 | 15 |  | 30 |  | 6 | 12 | 33.33%
7 | unm195 | Annai Violet Arts and Science College | 2026-01-09 | 2026-03-14 | 9:00–11:30 AM | 2.1 | 61 | Priyadharshini |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [36 empty] | 45 | 15 | 30 | 30 | 90 | 6 | 12 | 33.33%
[5 empty] | 11:40 AM–2:00 PM |  | 65 | [5 empty] | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [36 empty] | 45 | 15 |  | 30 |  | 6 | 12 | 33.33%
8 | unm1681 | St.Annes Arts and Science | 2026-01-07 | 2026-03-11 | 9:00 AM – 11:30 AM | 1.73 | 104 | Uday |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [38 empty] | 45 | 15 | 15 | 30 | 45 | 6 | 12 | 33.33%
9 | unm1353 | Anna Adarsh College | 2026-01-19 | 2026-03-21 | 10:00 AM – 12:30 PM | 5.68 | 98 | Janani | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1 | [41 empty] | 45 | 10 | 47.5 | 35 | 225 | 4 | 14 | 22.22%
[5 empty] | 10:00 AM – 12:30 PM |  | 73 |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [44 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
[5 empty] | 10:00 AM – 12:30 PM |  | 50 | [5 empty] | 1 | 1 |  |  |  |  | 1 | 1 | [42 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
[5 empty] | 2:00 PM – 4:30 PM |  | 50 |  | 1 | 1 | [5 empty] | 1 | [46 empty] | 45 | 7.5 |  | 37.5 |  | 3 | 15 | 16.67%
[5 empty] | 2:00 PM – 4:30 PM |  | 70 |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [44 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
10 | unm1435 | Thiruthangal Nadar College | 2026-01-12 | 2026-03-17 | 8.30 - 11 am | 4.5 | 138 | Peter | 1 | [5 empty] | 1 | 1 |  |  |  |  | 1 | [41 empty] | 45 | 10 | 40 | 35 | 180 | 4 | 14 | 22.22%
[8 empty] | Pugazh | 1 | [5 empty] | 1 | 1 |  |  |  |  | 1 | [41 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
[5 empty] | 11-1.30 pm |  | 132 |  | 1 | [5 empty] | 1 | 1 |  |  |  |  | 1 | [41 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
[9 empty] | 1 | [5 empty] | 1 | 1 |  |  |  |  | 1 | [41 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
11 | unm1485 | Soka Ikeda College of Arts and Science for Women | 2026-01-12 | 2026-03-20 | 9 am to 12:30 pm | 1.4 | 88 | Bhavani | 1 | [9 empty] | 1 |  |  | 1 |  |  | 1 | [37 empty] | 45 | 10 | 10 | 35 | 45 | 4 | 14 | 22.22%
12 | unm1739 | VALLAL P.T. LEE CHENGALVARAYA NAICKER ARTS AND SCIENCE COLLEGE (CO-EDN) | 2026-01-12 | 2026-03-20 | 9:30 AM – 12:00 PM | 1.68 | 51 | Uday | 1 | [5 empty] | 1 |  |  |  | 1 | [6 empty] | 1 | 1 | [35 empty] | 45 | 12.5 | 25 | 32.5 | 90 | 5 | 13 | 27.78%
[5 empty] | 12:30 pm to 2:30 pm |  | 50 |  | 1 | [5 empty] | 1 |  |  |  | 1 | [6 empty] | 1 | 1 | [35 empty] | 45 | 12.5 |  | 32.5 |  | 5 | 13 | 27.78%
13 | unm1487 | Jaya Govind | 2026-01-12 | 2026-03-12 | 9:00 AM – 11:30 AM | 1.28 | 77 | Nagadinesh | 1 | [5 empty] | 1 |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 | [35 empty] | 45 | 12.5 | 12.5 | 32.5 | 45 | 5 | 13 | 27.78%
Subhash
14 | unm1621 | Shri Shankarlal Sundarbai Shasun Jain College for Women | 2026-01-21 | 2026-04-02 | 9:00 AM – 11:00 AM | 3.33 | 50 | Balaji |  |  | 1 |  |  | 1 |  |  |  | 1 | [44 empty] | 45 | 7.5 | 30 | 37.5 | 180 | 3 | 15 | 16.67%
[5 empty] | 10:30 AM – 12:40 PM |  | 50 |  |  |  | 1 |  |  | 1 |  |  |  | 1 | [44 empty] | 45 | 7.5 |  | 37.5 |  | 3 | 15 | 16.67%
[5 empty] | 10:30 AM – 12:40 PM |  | 50 |  |  |  |  | 1 | [6 empty] | 1 | 1 | [42 empty] | 45 | 7.5 |  | 37.5 |  | 3 | 15 | 16.67%
[5 empty] | 3.30 pm to 5.50 pm |  | 50 |  |  |  |  | 1 | [6 empty] | 1 | 1 | [42 empty] | 45 | 7.5 |  | 37.5 |  | 3 | 15 | 16.67%
15 | unm1423 | Dr. MGR Janaki College of Arts & Science for Women. | 2026-01-27 | 2026-03-27 | 10:30 AM – 1:00 PM | 5.75 | 100 | Gayathri |  | 1 | 1 |  | 1 |  | 1 | [47 empty] | 45 | 10 | 40 | 35 | 180 | 4 | 14 | 22.22%
[5 empty] | 2:30 PM – 5:00 PM |  | 100 | Hema |  | 1 | 1 |  | 1 |  | 1 | [47 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
[5 empty] | 10:30 AM – 1:00 PM |  | 50 |  |  | 1 | 1 |  | 1 |  | 1 | [47 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
[5 empty] | 2:30 PM – 5:00 PM |  | 95 |  |  | 1 | 1 |  | 1 |  | 1 | [47 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
16 | unm1611 | Patrician College | 2026-01-19 | 2026-03-19 | 8:00–10:30 AM 10:30 AM–1:00 PM | 4.08 | 97 | Vishnu | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 |  |  | 1 | [41 empty] | 45 | 20 | 40 | 25 | 45 | 8 | 10 | 44.44%
[7 empty] | 44 | Divya
[7 empty] | 46 | Nikileshwari | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 |  |  | 1 | [41 empty] | 45 | 20 |  | 25 | 45 | 8 | 10 | 44.44%
29
29
17 | unm133 | Asan Memorial | 2026-01-22 | 2026-03-20 | 11 am to 1:15 pm | 1.46 | 49 | Subhash |  |  |  | 1 | 1 |  |  |  | 1 |  | 1 | [43 empty] | 45 | 10 | 20 | 35 | 45 | 4 | 14 | 22.22%
[5 empty] | 2 pm to 4:30 pm |  | 39 |  |  |  |  | 1 | 1 |  |  |  | 1 |  | 1 | [43 empty] | 45 | 10 |  | 35 | 45 | 4 | 14 | 22.22%
18 | unm1401 | Bhaktavatsalam Memorial College for Women | 2026-01-27 | 2026-03-27 | 9:30 AM – 12:00 PM | 1.4 | 43 | Harini |  | 1 |  |  | 1 | [49 empty] | 45 | 5 | 10 | 40 | 90 | 2 | 16 | 11.11%
[5 empty] | 12:30 PM – 3:00 PM |  | 45 |  |  | 1 |  |  | 1 | [49 empty] | 45 | 5 |  | 40 |  | 2 | 16 | 11.11%
19 | unm1699 | Avichi | 2026-01-27 | 2026-03-26 | 11:30 AM – 1:30 PM | 1.65 | 50 | Bhavani | 1 |  |  | 1 | [50 empty] | 45 | 5 | 10 | 40 | 90 | 2 | 16 | 11.11%
[7 empty] | 49 |  | 1 |  |  | 1 | [50 empty] | 45 | 5 |  | 40 |  | 2 | 16 | 11.11%
20 | unm1727 | St george | 2026-01-19 | 2026-03-23 | 9.00 am to 11.30 am | 0.55 | 33 | Balaji | 1 | 1 | [5 empty] | 1 |  |  |  | 1 | 1 | [41 empty] | 45 | 12.5 | 12.5 | 32.5 | 45 | 5 | 13 | 27.78%
21 | unm1687 | DON BOSCO COLLEGE OF ARTS AND SCIENCE, KILPAUK, CHENNAI - 600 010 | 2026-01-28 | 2026-03-25 | 8:30 AM to 11:00 AM | 0.3 | 18 | Peter |  |  | 1 |  | 1 | [49 empty] | 45 | 5 | 5 | 40 | 45 | 2 | 16 | 11.11%
22 | unm1437 | MAR GREGORIOS COLLEGE | 2026-01-20 | 2026-03-18 | 8:30 am to 11 am | 2.6 | 80 | Udaya |  | 1 |  | 1 |  |  |  | 1 |  | 1 | [44 empty] | 45 | 10 | 20 | 35 | 90 | 4 | 14 | 22.22%
[5 empty] | 12:30 pm to 2.00 pm |  | 80 |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [45 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
23 | unm1659 | SHRI KRISHNASWAMY COLLEGE FOR WOMEN, ANNA NAGAR, CHENNAI - 600 040. | 2026-01-22 | 2026-03-12 | 8:30 am to 11 am | 3.66 | 113 | Kiruthiga |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [43 empty] | 45 | 10 | 20 | 35 | 90 | 4 | 14 | 22.22%
[5 empty] | 11.30 AM to 2 pm |  | 113 | Priyadharshini |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [43 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
24 | unm1369 | GURU SHREE SHANTIVIJAI JAIN COLLEGE FOR WOMEN, VEPERY, CHENNAI-600 007. | 2026-02-05 | 2026-03-27 | 1:30 to 3 pm | 0.43 | 26 | Angel | [54 empty] | 45 | 0 | 0 | 45 | 45 | 0 | 18 | 0%
25 | UNM1441 | SREE MUTHUKUMARASWAMY COLLEGE | 2026-01-19 | 2025-03-26 | 9 am to 11:30 am | 2.33 | 70 | Nagadinesh | 1 | [8 empty] | 1 | 1 | [43 empty] | 45 | 7.5 | 15 | 37.5 | 90 | 3 | 15 | 16.67%
[5 empty] | 12.30 pm to 3 pm |  | 70 |  | 1 | [8 empty] | 1 | 1 | [43 empty] | 45 | 7.5 |  | 37.5 |  | 3 | 15 | 16.67%
26 | unm1475 | SRI KANYAKA PARAMESWARI ARTS and SCIENCE COLLEGE FOR WOMEN, CHENNAI-1 | 2026-01-19 | 2026-03-23 | 9 am to 12 pm | 1.65 | 50 | Gokulakrishnan | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1 | [41 empty] | 45 | 10 | 20 | 35 | 90 | 4 | 14 | 22.22%
[5 empty] | 12:30 to 3 pm |  | 49 |  | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1 | [41 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
27 | unm1330 | CHELLAMMAL WOMEN'S COLLEGE, GUINDY, CHENNAI | 2026-01-19 | 2026-03-19 | 2pm to 4:30 pm | 0.83 | 50 | Subhash | 1 |  |  | 1 | [6 empty] | 1 | [43 empty] | 45 | 7.5 | 7.5 | 37.5 | 45 | 3 | 15 | 16.67%
28 | unm1425 | KUMARARANI MEENA MUTHIAH COLLEGE OF ARTS and SCIENCE Co-Ed CHENNAI 20 | 2026-01-19 | 2026-03-23 | 8:30 am to 11 am | 0.78 | 47 | Subhash | 1 |  |  | 1 | [5 empty] | 1 |  |  | 1 | [41 empty] | 45 | 10 | 10 | 35 | 45 | 4 | 14 | 22.22%
29 | unm1429 | Alpha Arts and Science College | 2026-01-22 | 2026-03-20 | 9 to 11.30 | 3.88 | 78 | Gokul |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [43 empty] | 45 | 10 | 30 | 35 | 135 | 4 | 14 | 22.22%
[5 empty] | 10.30 to 1 |  | 78 | peter |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [43 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
[5 empty] | 2 to 4.30 |  | 77 | madhan |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [43 empty] | 45 | 10 |  | 35 |  | 4 | 14 | 22.22%
[7 empty] | 4208 | [55 empty] | 2970 | 725 | 725 | 2245 | 2970 | 290 | 898
522

## Summary
Category | Enrolled Count | Completed Count | In Progress | Not Started
Total Count | 4208 | 0 | 4182 | 26